## ProjectSchedule
PROJECT PLANNING TO BECOME PYTHON DEVELOPER
[FPT_Software_Internship] |  | Project Start: | 2024-02-15
[Python DeVeloper] |  | Today: | 2024-04-24
|  | Display Week: | 12 |  |  | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17
 | time axis 2024-04-29 to 2024-06-23
TASK | DESCRIPTION | PROGRESS | START | END | DAYS | time axis 2024-04-29 to 2024-06-23
1.Initiation | Requirement and Design
1.1 Complete a Prep Course | Learn everything about Python and gain a lot of useful insights into the field | 100% | 2024-05-01 | 2024-05-12 | 12
1.2 Learn the Basics of Python | Learning how it works avoid common mistakes and save time in the long run | 80% | 2024-05-01 | 2024-05-12 | 13
1.3 Determine the Type of Python Developer | Data Scientist & Machine Learning Engineer / Artificial Intelligence Engineer | 70% | 2024-05-07 | 2024-05-12 | 5
1.4 Choose a Learning Path | Online Courses & YouTube Videos | 70% | 2024-05-07 | 2024-05-12 | 5
1.5 Explore Python Frameworks | Familiar the language’s syntax and structure, better understand how to develop programs | 70% | 2024-05-13 | 2024-05-26 | 13
2.Hone the Essential Skills | Development | 80% | 2024-05-27 | 2024-06-30 | 13
2.1 Technical Skills |  | 80% | 2024-05-27 | 2024-06-30 | 13
2.1.1 Understanding of Multi-Process Architecture | object-oriented programming (OOP) concepts & practices and design patterns | 70% | 2024-05-27 | 2024-06-02 | 7
2.1.2 Python Frameworks | web development frameworks such as Flask, Django, and Pyramid | 70% | 2024-05-27 | 2024-06-02 | 7
2.1.3 Python Libraries | Using these code templates to create applications faster | 70% | 2024-05-27 | 2024-06-02 | 7
2.1.4 Frond-End Technology | Familiarity with back-end and front-end technologies | 70% | 2024-05-27 | 2024-06-09 | 14
2.1.5 Machine Learning & AI | Research, implement ,Train, fine tune and Deploy Machine Learning Models to production environments | 70% | 2024-06-03 | 2024-06-16 | 13
2.1.6 Deep Learning | Deep learning from first principles, Setting up your own deep-learning environment, Image-classification models | 70% | 2024-06-03 | 2024-06-09 | 13
2.1.7 Version Control | Working knowledge of version control systems (Git, SVN, etc.) | 70% | 2024-06-03 | 2024-06-16 | 13
2.1.8 Familarity with ORM libraries | Using ORMs can continue to write in Python code to create and update data schemas. | 70% | 2024-06-10 | 2024-06-16 | 6
2.1.9 Analytical Skills | Analytical Skills with a Solid Understanding of Multi-Process Architecture | 70% | 2024-06-17 | 2024-06-30 | 13
2.1.10 Design Skills | Design scalable products, implement servers in such a way that they are highly available | 70% | 2024-06-17 | 2024-06-30 | 13
2.1.11 Expertise in Code Python | refers to the Python programming language and Having in-depth knowledge of this subject . | 80% | 2024-06-17 | 2024-06-30 | 13
2.2 Soft Skills |  | 90% | 2024-07-01 | 2024-08-04 | 3
2.2.1 Communication | making sure your code is well-documented and easy for other people to read | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.2 Organization | Being able to organize files, folders, and databases efficiently so that the team can quickly locate important information | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.3 Time Management | These skills also help professionals prioritise tasks within a programming assignment | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.4 Problem and Solving Skills | Creative solutions if the problem is more complex than expected, or they may have to find potential flaws in their code. | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.5 Presentation Skill | Effective communication with clients can help you resolve several issues and propel your business forward. | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.6 Multi-tasking | Having good time-management skills enables to organise work and prioritise tasks to stay productive | 80% | 2024-07-01 | 2024-08-04 | 3
2.2.7 Web development | Website development and design are essential in the modern technology world | 80% | 2024-07-01 | 2024-08-04 | 3
3. Build Porfolio and Create Github Profile | Deloyment and Testing | 100% | 2024-07-01 | 2024-08-01 | 30
3.1 Create Github Profile |  | 90% | 2024-07-01 | 2024-08-01 | 30
3.1.1 Build Your GitHub Repository | Add your Python projects and practice work to your GitHub repository | 90% | 2024-07-01 | 2024-07-07 | 7
3.1.2 Write Readable Code | guidelines available to help you write readable code, including PEP 8 style guidelines | 90% | 2024-07-01 | 2024-07-14 | 14
Indentation, Tabs and spaces, Maximum line length |  | 90% | 2024-07-01 | 2024-07-14 | 14
Line breaks, Blank lines, Source file encoding |  | 90% | 2024-07-01 | 2024-07-14 | 14
String quotes,White spaces in expressions,Trailing commas,Naming conventions |  | 90% | 2024-07-01 | 2024-07-14 | 14
3.1.3 Create Proper Documentation | Proper documentation helps improve code readability. Keep in mind that you should include a README file within your GitHub repository. | 90% | 2024-07-01 | 2024-07-07 | 7
3.1.4 Read books on Python Coding | there’s always something new to learn and more you know, the more your confidence increases. | 90% | 2024-07-01 | 2024-07-07 | 7
3.1.5 Grow Your Python Skillset | something new to learn & the more you know, the more your confidence increases | 90% | 2024-07-01 | 2024-07-07 | 7
3.1.6 Master AI and Machine Learning with Python | Some of the most crucial Python applications are in the fields of Artificial Intelligence (AI) and Machine Learning. | 90% | 2024-07-01 | 2024-07-07 | 7
3.1.7 Start a Blog and Write about What You Have Learned | materials you used to collect information, what projects you worked on | 90% | 2024-07-01 | 2024-07-14 | 14
3.1.8 Make Open Source Contributions | make contributions to associated projects | 90% | 2024-07-01 | 2024-07-09 | 8
3.1.9 Follow Daily Schedule For Practice | Taking out some time every day to write code so that every aspect of Python is at your fingertips. | 90% | 2024-07-01 | 2024-07-10 | 9
3.2 Build Porfolio |  | 90% | 2024-07-01 | 2024-07-11 | 10
3.2.1 Organizing files, keeping track of digital collections, or training a neural network | Use GitHub (or any online repository) | 90% | 2024-07-01 | 2024-07-12 | 11
3.2.2 Visualize your data and projects with graphs, bar charts and more | Keep track of project using GitHub’s issue tracker | 90% | 2024-07-01 | 2024-07-13 | 12
3.2.3 Add projects to a portfolio | Submit pull requests | 90% | 2024-07-01 | 2024-07-14 | 13
3.2.4 Enroll in a Python Programming To Porforlio | Use feature branches & Write an informative readme | 90% | 2024-07-01 | 2024-07-15 | 14
4. Tools Do Python Developers Use | Review | 80% | 2024-07-15 | 2024-07-21 | 14
4.1 Keras | It is an open-source, high-level neural grid library written in Python, and based on four principles | 70% | 2024-07-15 | 2024-07-17 | 2
4.2 PyCharm IDE | PyCharm gives reliable intelligent automated code refactoring, testing assistance, and inspection. | 70% | 2024-07-15 | 2024-07-18 | 3
4.3 Python Anywhere | The hosting is decentralized, which assists in remote research, learning, and development. | 70% | 2024-07-15 | 2024-07-19 | 4
4.4 Pip Package | This tool is python’s default package manager and has pre-installation. | 70% | 2024-07-15 | 2024-07-20 | 5
4.5 Jupyter Notebook | This tool lets you insert mathematical inscriptions within markdown compartments. | 70% | 2024-07-15 | 2024-07-21 | 6
5. Become A Python Developer | Evaluate | 80% | 2024-08-01 | 31/08//2024 | 30
5.1 Keep up to date on your subject | numerous resources that can teach you the latest developments in Python and software engineering | 70% | 2024-08-01 | 2024-08-04 | 3
5.2 Grow skill set | develop your skills by learning about different Python libraries | 70% | 2024-08-01 | 2024-08-05 | 4
5.3 Practise machine-learning knowledge | Practising your machine-learning algorithms can help you move up to better-paid roles | 70% | 2024-08-01 | 2024-08-11 | 10
5.4 Contribute to open-source projects | Open-source software is publicly accessible code that anyone can see | 70% | 2024-08-01 | 2024-08-18 | 24
|  | 70% | 2024-08-01 | 2024-08-25 | 24
Insert new rows ABOVE this one
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.